FLIGHT DATA ANALYSIS INTERNSHIP

WEEK 1			: 	PLANNING

Data Analysis	 	: 	Analyzing flight data and observing patterns that 						emerges

DOCUMENT AND TRAINEE DETAILS

| Prepared by | Eliudi Elphace Tonda |
| --- | --- |
| Date | 06th October 2026 |
| Purpose | Analyzing flight data and observing patterns from it |
| Duration | 4 weeks ( 2th October 2026 - 30th October 2026) |
| Role | Flight Data Analysis |

CONTENTS

- Internship Overview

- Role and problem Overview

- How professionals approach flight data analysis

- The core - Scope of the problem

- Tools and Software used

- Risks and Documentation plan

- References

- OVERVIEW

- This is a four weeks internship which is focused mainly on flight data analysis and here is a week 1 planning document for a whole internship. In this document no data has been analyzed because it gives the do(s) and don’t(s) in the whole process. Throughout the process I will thoroughly consider flight parameters, standards guide and professional ways to evaluate each data in the coming weeks.

- The set parameters such as altitude , speeds,engine configurations and accelerations from publicly available datasets will be my foundation and everything will be properly documented. Testing data quality of parameters will give a quality result in the analysis and each step of the way everything from code , assumptions, weekly reports and datasets will be published on my GitHub .

- Weekly plan

| - Week | - Focus | - Main task | - Output |
| --- | --- | --- | --- |
| - 1 | - Planning and study of parameters | - Research and full internship planning | - This document |
| - 2 | - Data processing | - Downloading open data , building a parameter dictionary, converting units and time base , segment flight bases and computing baseline statistics | - Parameter dictionary,cleaning log , code on GitHub |
| - 3 | - Event detection and validation | - Implementing isolation forest to compare with checks in tables and estimating errors | - Analyzing document . comparison table |
| - 4 | - Final report and an overall presentation | - Summary of week 1 to 4 and how they correlate | - Final report , final repository and final presentation |

- 2.ROLE AND PROBLEM OVERVIEW

- 2.1 What is the core responsibilities of a flight data analyst?

- Aircraft usually records hundreds and thousands of parameters continuously . Operators and analysts use these data without waiting for an incident. Any flight data analyst

- Receives downloaded data from quick access recorder or a flight data recorder and then starts data conversion from raw data to chunks of engineering units

- Checks if the data is valid  before starting hands on the particular data

- Runs a detection algorithm to identify if there is a mismatch in any event such as higher rate of descend or lower rate of climb

- Protects the crew identity after the results finding

- Checks trends and patterns between certain types of aircraft, airports or even runways

- 2.2 What is the Source of data

- Each aircraft is equipped with sensors and avionics which send data over digital buses known as ARINC 429 to a data collection facility. At the unit this data will then be formatted into continuous data frames known as ARINC 717 or day to day recorders which are written in a crash protected method and for a quick access after being decoded.

- In this whole internship the type of data used is already decoded data ready to be used because I do not have any airlines data access so throughout is a publicly accessible data with respect to their license of use. These data is arleady decoded and turned into counts such as feet , knots and degrees.

- 2.3 Why the study of parameter comes first?

- Each result count traces back to a parameter stud, any misread of units, confusing a sampling rate or trusting a stuck sensor causes huge cost in terms o outcome. Data validation in each parameter is something that I will be considering before any data processing.

- 3.HOW PROFESSIONALS APPROACH

- PARAMETER STUDY

- Each professional examines the recorded flight parameters and establishes similarities and differences in terms of units and their implication to obtain different rates and easy quantification.

- 3.1 Accepted steps and their sources

| - Step | - How professionals handle | - Technique | - Source/Reason |
| --- | --- | --- | --- |
| - Converting raw data to engineering units | - Documenting each data conversion | - Linear and polynomial equations and bit decoding for discrete data | - ARINC717 or manufacturer documentation |
| - Validate data quality | - Checking and validating every parameter before using | - Range,rate of change,flat line gap etc | - ICAO doc10000 - FDM practice |
| - Segment flight phases | - Label each sample with a phase so thresholds apply in the right context. | - Rule-based labels from altitude, speed, weight-on-wheels, gear, flaps. | - CICTT phase of flight definitions; operator FDM rules. |
| - Establishing foundation | - Learning how normal data looks | - Looking for mean,median,percentiles and even distributions | - ICAO doc 10000 - statistical analysis |
| - Detecting events | - Checking the overlapping limits | - Each parameter has its height window and it should be rechecked | - ICAO doc 10000 , FAA AC |
| - Searching for the unexpected | - Going outside the box looking for the flight behaviour which are not covered | - Outliers finding ,isolation forest, clusturing etc | - Liu et al 2008 , Das et al 2010 , Basora et al 2019 |
| - Review | - Validating results and protecting confidentiality | - Reducible scripts and identify outputs | - ICAO Annex 19 , Doc 10000 |

3.2    Core parameters of study

The list below is the working set. Sample rates and ranges are indicative values for a transport aircraft.

| Parameter | Unit | Rate | Why matters | Validity check |
| --- | --- | --- | --- | --- |
| Pressure altitude | ft | 1 Hz | Flight profile, phase detection, climb and descent | Plausible range; smooth change; consistent with vertical speed. |
| Radio altitude | Ft | 1Hz | High above on approach and landing | Valid below 2500 ft |
| Computed airspeed | kt | 1 Hz | Speed control, stall margin, approach speed | No negative values; no jumps larger than physically possible. |
| Ground speed | Kt | 1Hz | Taxi and runway speed and wind effects | Comparing with speed derived from latitude and longitude |
| Vertical speed | Ft/min | 1Hz | Descent rate or approach | Comparing ith the altitude derivative |
| Pitch altitude | deg | 4Hz | Rotation , fare , tail strike | Range check g and spike detection |
| Roll attitude | deg | 4 Hz | Bank angle in turns and on approach | Range check; spike detection. |
| Magnetic heading | Deg | 1Hz | Run way alignment and track | Handle 0-360 wrap around before statistics |
| Normal acceleration | g | 8 Hz | Landing load, turbulence | About 1 g when level; high rate needs care when resampling. |
| Engine N1 and N2 | % | 1Hz | Thrust setting , take off and go around power | Range 0 -110% amd comparing left and right engine |
| Flap position | deg or setting | 1 Hz or lower | Configuration on take-off and approach | Only expected values; changes in expected order. |
| Landing gear | Discrete | 1 Hz or lower | Configuration, approach stability | Altitude and phase |
| Weight on wheels | discrete | 1 Hz or lower | Ground versus air, touchdown time | Logic with radio altitude and speed. |
| Time UTC | 5 | 1Hz | Common time base for all parameters | No duplicates or gaps |

All these data should undergo data quality checks before analysisalso the result of each check is recorded and a reader can see how much data was excluded

3.3 Flight phase segmentation

A threshold that is sensible on approach may be meaningless on the ground, so every sample needs a phase label. The common phase vocabulary comes from the CAST/ICAO Common Taxonomy Team (CICTT): standing, taxi, take-off, initial climb, en-route climb, cruise, descent, approach, landing and go-around. My segmentation will be rule-based and easy to inspect, using weight-on-wheels, altitude, vertical speed, ground speed, gear and flap state. I will check the result visually on a sample of flights, since automatic labels fail in unusual profiles such as go around and low level flights.

3.4 Event detection and anomaly screening

Operators typically run rule-based events: for example, descent rate above a limit below a given height, or speed outside a window relative to the approach reference speed. Each rule has a threshold, a duration or height window and often several severity levels. A reviewer then confirms whether a flagged flight is a real event or a data problem.

Rules only find what someone has already thought of, so research also uses statistical and machine learning screening to find unusual flights. Examples include Isolation Forest , clustering of flights by phase profile, and multiple-kernel anomaly detection developed at NASA. I will use one simple, explainable method and compare it with the rule based result.

3.7 Professional practice I will follow

- Validate before analyzing. No event counts are reported until quality checks are complete.

- Document every parameter and threshold, including its source, so decisions can be traced.

- Keeping a person in the loop. Flagged items are screening results, not conclusions.

- Protect confidentiality. Outputs will not identify crews, and I will respect licence terms of the data I use.

- Making work repeatable.

4. Scope of the problem

4.1 Problem statement

How can a set flight parameters from flight data set be understood, validated and used to characterize normal behaviour by phase of flight, and how can that baseline be used to flag unstable or unusual approaches?

4.2 In scope and out of scope

| In scope | Out of scope |
| --- | --- |
| Parameter dictionary for core parameters. | Decoding raw ARINC 717 bit streams or recorder binary files. |
| Data quality assessment | Investigation about the cause |
| Approach and landing event screening | Engine health and maintenance prediction |
| GitHub repository, a final report and a short presentation. | Fleet level or airline pecific conclusions. |
| Comparison of results on published data | Real time analysis |

4.3 Assumptions

- A  public dataset with multiple flights and documented parameters is available. My first choice is the NASA DASHlink collection "Flight Data For Tail_ 670_1.zip"  The catalogue lists it as public, with no licence information provided, and I will state this in my dataset note.

- The data is already decoded into engineering units, and the dataset documentation describes parameter names and units.

- Thresholds taken from public guidance for example the Flight Safety  stabilized approaches are good enough for screening, but will be adapted if the dataset is general aviation rather than transport category.

- The internship lasts four weeks and each week has a defined task: Week 1 planning, Week 2 data processing, Week 3 anomaly detection and validation, Week 4 final report and a presentation of under ten minutes.

4.4 Constraints

- No  access to airline recorder data, so findings describe the chosen dataset and cannot be generalized to a specific airline

- Four  weeks in total, so the project uses one tail's worth of data

- Public  data usually has no confirmed event labels, so detection results cannot be scored as precisely as in a production programme; I will use manual review of samples instead.

- Compute and tools: a standard laptop and free software only.

- 5.TOOLS AND SOFTWARE USED

| - Tool | - Use | - Reason |
| --- | --- | --- |
| - Python 3 with jupyter | - Analysis environment | - Free and widely used for data work due to its reliable libraries |
| - Pandas and numpy | - Loading , cleaning and re-sampling of data | - Handles gaps and time series |
| - Scipy | - Statistical tests and filtering | - Arranges the data well for engineering analysis |
| - Scikit-learn | - Running isolation forest and simple clustering | - Documenting simple models |
| Matplotlib and Plotly | Static and interactive plots of flight profiles. | Static plots for the report; interactive plots help review individual flights. |
| Excel or CSV files | Parameter dictionary and cleaning log | Readable by non-programmers and easy to review |
| Git and Github | Version control and public project repository | It gives history of changes also it is required in this internship |

- 6.RISKS AND DOCUMENTATION PLAN

- Week 1 has established that parameter study is the foundation of flight data analysis: parameters must be defined, converted, validated and put in phase context before events can be trusted. My plan applies that professional sequence on a manageable scale, using open data, documented standards, transparent rules and one explainable statistical method. Though here are the risks and mitigation.

| - Risk | - Likelihood | - Mitigation |
| --- | --- | --- |
| - Lack of some core parameters in a chosen dataset | - Medium | - Checking the parameter list before starting in week 2 |
| - Time shortage for deep analysis | - High | - Time management |
| - There is no ground truth for the events | - high | - Manual reviews |
| Thresholds from transport aircraft do not suit the dataset. | Medium | Make thresholds configurable; justify each change. |

- Documentation plan

- data/raw/			:	original raw files without being edited

- data/processed		:	cleaned and re sampled data

- docs/				:	parameter dictionary and weekly reports

- src/				:	python modules , plotting and event rules and 						notebooks

- results/			:	tables and figures built by the pipeline

- requirements.txt		:	software used

- README.md		:	whole internship format as it progresses

7.REFERENCES

- NASA dash link for dataset at https://c3.ndc.nasa.gov/dashlink/resources/648/

- ICAO Doc 10000, Manual on Flight Data Analysis Programmes (FDA

- ICAO Annex 6, Part I (flight recorders)

- EUROCAE ED-112A

- Das, Matthews, Srivastava and Oza (2010), multiple kernel anomaly detection, ACM KDD

- Liu, Ting and Zhou (2008), Isolation Forest, IEEE ICDM

- EU Regulation 965/2012 (ORO.AOC.130)